## Tabelle1
Country | Company Code | MaintPlant | Main WorkCtr | Functional Loc. | Description | Equipment | Description | Order Type | Order | Description | MaintActivType | Priority | Priority | Group | Group Counter | Created on | System status | User status | Oper.WorkCenter | Control key | Oper./Act. | Opr. short text | Work | Number | Normal duration | Norm.duratn un. | Actual work | Unit for work | Bas. start date | Basic fin. date | Sched. start | Sched. finish | Earl.start date | EarliestEndDate | Latest start | Lat.finish date | Actual start | Act.finish date | Op.SystemStatus | Oper.UserStatus
DE | 465C | BS01 | DE_OFFDT | DB0388-029 | WT DT29 DanTysk (3601210) | 012345678911 | WT Dan Tysk ,DT29 (3601210) | ZCS5 | 12345678 | A9B10196358 Retrofit non-phys Fix earth | 040 |  |  |  |  | 2017-10-10 | REL CCOK NMAT PRC SETC | ZBNQ PERF RECV ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10196358 Retrofit non-phys Fix earth | 0 | 0 | 0 | H | 0 | H | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-056 | WT DT56 DanTysk (3601237) | 012345678912 | WT Dan Tysk ,DT56 (3601237) | ZCS5 | 12345679 | DT56: UPS battery exchange | 040 |  |  |  |  | 2017-06-14 | CRTD MANC NMAT NTUP PRC | ZBNQ | DE_OFFDT | ZMR1 | 0010 | DT56: UPS battery exchange | 4 | 2 | 2 | H | 0 | H | 2018-06-14 | 2018-06-14 |  |  | 2017-06-14 | 2017-06-14 | 2017-06-13 | 2017-06-13 |  |  | CRTD
DE | 465C | BS01 | DE_OFFDT | DB0388-035 | WT DT35 DanTysk (3601216) | 012345678913 | WT Dan Tysk ,DT35 (3601216) | ZCS5 | 12345680 | DT35: UPS battery exchange | 040 |  |  |  |  | 2017-06-14 | CRTD MANC NMAT NTUP PRC | ZBNQ | DE_OFFDT | ZMR1 | 0010 | DT35: UPS battery exchange | 4 | 2 | 2 | H | 0 | H | 2018-06-14 | 2018-06-14 |  |  | 2017-06-14 | 2017-06-14 | 2017-06-13 | 2017-06-13 |  |  | CRTD
DE | 465C | BS01 | DE_SANDB | DB0411-018 | WT SB18 Sandbank (4000349) | 012345678914 | WT Sandbank ,SB18 (4000349) | ZCS5 | 12345681 | exchange rubber bellows | 040 |  |  |  |  | 2017-07-03 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | exchange rubber bellows | 6 | 3 | 2 | H | 0 | H | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-062 | WT SB64 Sandbank (4000393) | 012345678911 | WT Sandbank ,SB64 (4000393) | ZCS5 | 12345682 | SB64 TS Outlet socket in tower | 040 |  |  |  |  | 2017-07-07 | REL PCNF CCOK NMAT PRC RESA SETC | ZBNQ CLAR PERF ZBMC | DE_SANDB | ZMR1 | 0010 | SB64 TS Outlet socket in tower | 4 | 2 | 2 | H | 2 | H | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | PCNF REL
DE | 465C | BS01 | DE_SANDB | DB0411-072 | WT SB80 Sandbank (4000403) | 012345678912 | WT Sandbank ,SB80 (4000403) | ZCS5 | 12345683 | Exchange Rubber Bellow | 040 |  |  |  |  | 2017-07-14 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Exchange Rubber Bellow | 6 | 3 | 2 | H | 0 | H | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-069 | WT SB77 Sandbank (4000400) | 012345678913 | WT Sandbank ,SB77 (4000400) | ZCS5 | 12345684 | Exchange Rubber Bellow | 040 |  |  |  |  | 2017-07-14 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Exchange Rubber Bellow | 6 | 3 | 2 | H | 0 | H | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 | 2017-07-14 | 2017-07-15 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-056 | WT SB58 Sandbank (4000387) | 012345678914 | WT Sandbank ,SB58 (4000387) | ZCS5 | 12345685 | Water Ingress Tower Ligth | 040 | 2 | Normal |  |  | 2017-07-21 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Water Ingress Tower Ligth | 6 | 3 | 2 | H | 0 | H | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-054 | WT SB56 Sandbank (4000385) | 012345678911 | WT Sandbank ,SB56 (4000385) | ZCS5 | 12345686 | SB56: broke plugs on Hiab Crane | 040 |  |  |  |  | 2017-07-25 | REL CCOK NMAT PRC SETC | ZBNQ CLAR PERF | DE_SANDB | ZMR1 | 0010 | SB56: broke plugs on Hiab Crane | 6 | 3 | 2 | H | 0 | H | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-069 | WT SB77 Sandbank (4000400) | 012345678912 | WT Sandbank ,SB77 (4000400) | ZCS5 | 12345687 | exchange rubber bellows | 040 |  |  |  |  | 2017-07-31 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | exchange rubber bellows | 6 | 3 | 2 | H | 0 | H | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-043 | WT SB44 Sandbank (4000374) | 012345678913 | WT Sandbank ,SB44 (4000374) | ZCS5 | 12345688 | Boom Extension on Hiab Crane | 040 | 2 | Normal |  |  | 2017-05-30 | REL CCOK MSPT PRC SETC | ZBNQ CLAR PERF ZBA1 ZBPO | DE_SANDB | ZMR1 | 0010 | Boom Extension on Hiab Crane | 6 | 2 | 3 | H | 0 | H | 2017-06-20 | 2017-08-07 | 2017-06-20 | 2017-08-07 | 2017-06-20 | 2017-08-07 | 2017-06-20 | 2017-08-07 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-071 | WT SB79 Sandbank (4000402) | 012345678914 | WT Sandbank ,SB79 (4000402) | ZCS5 | 12345689 | Exchange Rubber Bellow | 040 |  |  |  |  | 2017-07-14 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Exchange Rubber Bellow | 6 | 3 | 2 | H | 0 | H | 2017-07-14 | 2017-08-15 | 2017-07-14 | 2017-08-15 | 2017-07-14 | 2017-08-15 | 2017-07-14 | 2017-08-15 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-015 | WT SB15 Sandbank (4000346) | 012345678911 | WT Sandbank ,SB15 (4000346) | ZCS5 | 12345690 | 10000 : No connection | 040 |  |  |  |  | 2017-08-15 | REL CCOK GMPS NMAT PRC RESA SETC | ZBNQ PERF RFCO ZBCC | DE_SANDB | ZMR1 | 0010 |  | 4 | 2 | 2 | H | 0 | H | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-038 | WT SB39 Sandbank (4000369) | 012345678912 | WT Sandbank ,SB39 (4000369) | ZCS3 | 12345691 | SB39 Remote stop - Owner | 030 |  |  |  |  | 2017-08-24 | REL CCOK NMAT PRC SETC | ZBNQ ZBMC | DE_SANDB | ZMR1 | 0010 | SB39 Remote stop - Owner | 1 | 2 | 0.5 | H | 0 | H | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-011 | WT DT11 DanTysk (3601192) | 012345678913 | WT Dan Tysk ,DT11 (3601192) | ZCS5 | 12345692 | A9B10191123 - Retrofit, yaw software 201 | 040 |  |  |  |  | 2017-11-10 | REL CCOK MACM PRC SETC | ZBNQ PERF RECV RFCO ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10191123 - Retrofit, yaw software 201 | 0 | 0 | 0 | H | 0 | H | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-060 | WT SB62 Sandbank (4000391) | 012345678914 | WT Sandbank ,SB62 (4000391) | ZCS5 | 12345693 | exchange rubber bellows | 040 | 1 | High |  |  | 2017-06-28 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | exchange rubber bellows | 4 | 2 | 2 | H | 0 | H | 2017-06-28 | 2017-08-28 | 2017-06-28 | 2017-08-28 | 2017-06-28 | 2017-08-28 | 2017-06-28 | 2017-08-28 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-001 | WT SB01 Sandbank (4000332) | 012345678911 | WT Sandbank ,SB01 (4000332) | ZCS5 | 12345694 | HIAB Crane: Troubleshooting | 040 | 2 | Normal |  |  | 2017-08-29 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | HIAB Crane: Troubleshooting | 2 | 1 | 2 | H | 0 | H | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-022 | WT SB22 Sandbank (4000353) | 012345678912 | WT Sandbank ,SB22 (4000353) | ZCS3 | 12345695 | Krima-2439613: Sabik UPS battery replace | 030 | 2 | Normal |  |  | 2017-06-30 | REL CCOK NMAT PRC SETC | ZBNQ PERF ZBMC | DE_SANDB | ZMR1 | 0010 | Krima-2439613: Sabik UPS battery replace | 4 | 2 | 2 | H | 0 | H | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-059 | WT SB61 Sandbank (4000390) | 012345678913 | WT Sandbank ,SB61 (4000390) | ZCS3 | 12345696 | Krima-2439613: UPS batteries replacement | 030 | 2 | Normal |  |  | 2017-06-30 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Krima-2439613: UPS batteries replacement | 4 | 2 | 2 | H | 0 | H | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 | 2017-06-30 | 2017-08-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-078 | WT DT78 DanTysk (3601259) | 012345678914 | WT Dan Tysk ,DT78 (3601259) | ZCS1 | 12345697 | 3,00_WT-BS01 3601259 Yearly Crane Inspec | 020 |  |  | CRANE | 1 | 2016-05-29 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZSMC | 0010 | Crane inspection | 3 | 1 | 3 | H | 0 | H | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-078 | WT DT78 DanTysk (3601259) | 012345678911 | WT Dan Tysk ,DT78 (3601259) | ZCS1 | 12345698 | 3,00_WT-BS01 3601259 Yearly Crane Inspec | 020 |  |  |  |  | 2016-05-29 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601259 Yearly Crane Inspec | 3 | 1 | 3 | H | 0 | H | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 | 2017-08-19 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-040 | WT DT40 DanTysk (3601221) | 012345678912 | WT Dan Tysk ,DT40 (3601221) | ZCS1 | 12345699 | 3,00_WT-BS01 3601221 Yearly Lift Inspect | 020 |  |  | LIFT | 1 | 2016-09-04 | REL NMAT SETC | ZBNQ PERF RFCO | DE_OFFDT | ZSMC | 0010 | Lift inspection | 3 | 1 | 3 | H | 0 | H | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-040 | WT DT40 DanTysk (3601221) | 012345678913 | WT Dan Tysk ,DT40 (3601221) | ZCS1 | 12345700 | 3,00_WT-BS01 3601221 Yearly Lift Inspect | 020 |  |  |  |  | 2016-09-04 | REL NMAT SETC | ZBNQ PERF RFCO | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601221 Yearly Lift Inspect | 3 | 1 | 3 | H | 0 | H | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-040 | WT DT40 DanTysk (3601221) | 012345678914 | WT Dan Tysk ,DT40 (3601221) | ZCS1 | 12345701 | 3,00_WT-BS01 3601221 Yearly Crane Inspec | 020 |  |  | CRANE | 1 | 2016-09-04 | REL NMAT SETC | ZBNQ PERF RFCO | DE_OFFDT | ZSMC | 0010 | Crane inspection | 3 | 1 | 3 | H | 0 | H | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-040 | WT DT40 DanTysk (3601221) | 012345678911 | WT Dan Tysk ,DT40 (3601221) | ZCS1 | 12345702 | 3,00_WT-BS01 3601221 Yearly Crane Inspec | 020 |  |  |  |  | 2016-09-04 | REL NMAT SETC | ZBNQ PERF RFCO | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601221 Yearly Crane Inspec | 3 | 1 | 3 | H | 0 | H | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 | 2017-08-18 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-007 | WT DT07 DanTysk (3601188) | 012345678912 | WT Dan Tysk ,DT07 (3601188) | ZCS5 | 12345703 | A9B10170721 Retrofit Power Supply G4 | 040 |  |  |  |  | 2017-11-10 | REL CCOK GMPS MACM PRC RESA SETC | ZBNQ PERF RECV RFCO ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10170721 Retrofit Power Supply G4 | 0 | 0 | 0 | H | 0 | H | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-007 | WT DT07 DanTysk (3601188) | 012345678913 | WT Dan Tysk ,DT07 (3601188) | ZCS5 | 12345704 | A9B10196140 Retrofit, sign f dehumidifi | 040 |  |  |  |  | 2017-11-10 | REL CCOK GMPS NMAT PRC RESA SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10196140 Retrofit, sign f dehumidifi | 0 | 0 | 0 | H | 0 | H | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-059 | WT SB61 Sandbank (4000390) | 012345678914 | WT Sandbank ,SB61 (4000390) | ZCS5 | 12345705 | 0 : Damaged fiber optic cable | 040 | 2 | Normal |  |  | 2017-07-24 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBCC ZBMC | DE_SANDB | ZMR1 | 0010 | 0 : Damaged fiber optic cable | 4 | 2 | 2 | H | 0 | H | 2017-07-24 | 2017-09-01 | 2017-07-24 | 2017-09-01 | 2017-07-24 | 2017-09-01 | 2017-07-24 | 2017-09-01 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-027 | WT SB27 Sandbank (4000358) | 012345678911 | WT Sandbank ,SB27 (4000358) | ZCS5 | 12345706 | 0 : Hiab Crane Slow | 040 | 3 | Low |  |  | 2017-07-28 | REL CCOK NMAT PRC SETC | ZBNQ CLAR PERF RFCO ZBCC ZBMC | DE_SANDB | ZMR1 | 0010 | 0 : Hiab Crane Slow | 2 | 2 | 1 | H | 0 | H | 2017-07-27 | 2017-09-01 | 2017-07-27 | 2017-09-01 | 2017-07-27 | 2017-09-01 | 2017-07-27 | 2017-09-01 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-029 | WT SB29 Sandbank (4000360) | 012345678912 | WT Sandbank ,SB29 (4000360) | ZCS3 | 12345707 | Switching support Vattenfall | 030 |  |  |  |  | 2017-09-01 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | Switching support Vattenfall | 2 | 1 | 2 | H | 0 | H | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-061 | WT SB63 Sandbank (4000392) | 012345678913 | WT Sandbank ,SB63 (4000392) | ZCS5 | 12345708 | Inspection on Water Ingress | 040 | 2 | Normal |  |  | 2017-09-01 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | Inspection on Water Ingress | 1 | 2 | 0.5 | H | 0 | H | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-066 | WT SB68 Sandbank (4000397) | 012345678914 | WT Sandbank ,SB68 (4000397) | ZCS5 | 12345709 | Inspection on Water Ingress | 040 | 2 | Normal |  |  | 2017-09-01 | REL CCOK NMAT PRC SETC | ZBNQ RFCO ZBCC ZBMC | DE_SANDB | ZMR1 | 0010 | Inspection on Water Ingress | 1 | 2 | 0.5 | H | 0 | H | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-023 | WT SB23 Sandbank (4000354) | 012345678911 | WT Sandbank ,SB23 (4000354) | ZCS5 | 12345710 | Inspection on Water Ingress | 040 | 2 | Normal |  |  | 2017-09-04 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | Inspection on Water Ingress | 2 | 2 | 1 | H | 0 | H | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-075 | WT DT75 DanTysk (3601256) | 012345678912 | WT Dan Tysk ,DT75 (3601256) | ZCS5 | 12345711 | A9B10191123 - Retrofit, yaw software 201 | 040 |  |  |  |  | 2017-11-10 | REL CCOK MACM PRC SETC | ZBNQ PERF RECV ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10191123 - Retrofit, yaw software 201 | 0 | 0 | 0 | H | 0 | H | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-061 | WT SB63 Sandbank (4000392) | 012345678913 | WT Sandbank ,SB63 (4000392) | ZCS5 | 12345712 | No Connection | 040 | 3 | Low |  |  | 2017-09-19 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO ZBMC | DE_SANDB | ZMR1 | 0010 | No Connection | 2 | 2 | 1 | H | 0 | H | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-064 | WT DT64 DanTysk (3601245) | 012345678914 | WT Dan Tysk ,DT64 (3601245) | ZCS1 | 12345713 | 3,00_WT-BS01 3601245 Yearly Crane Inspec | 020 |  |  | CRANE | 1 | 2016-05-08 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0010 | Crane inspection | 3 | 1 | 3 | H | 0 | H | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-064 | WT DT64 DanTysk (3601245) | 012345678911 | WT Dan Tysk ,DT64 (3601245) | ZCS1 | 12345714 | 3,00_WT-BS01 3601245 Yearly Crane Inspec | 020 |  |  |  |  | 2016-05-08 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601245 Yearly Crane Inspec | 3 | 1 | 3 | H | 0 | H | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-064 | WT DT64 DanTysk (3601245) | 012345678912 | WT Dan Tysk ,DT64 (3601245) | ZCS1 | 12345715 | 3,00_WT-BS01 3601245 TMSE | 020 |  |  | TMSE | 1 | 2016-05-08 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZSMC | 0010 | Turbine mounted safety equipment | 3 | 1 | 3 | H | 0 | H | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-064 | WT DT64 DanTysk (3601245) | 012345678913 | WT Dan Tysk ,DT64 (3601245) | ZCS1 | 12345716 | 3,00_WT-BS01 3601245 TMSE | 020 |  |  |  |  | 2016-05-08 | REL NMAT SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601245 TMSE | 3 | 1 | 3 | H | 0 | H | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 | 2017-08-25 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-020 | WT DT20 DanTysk (3601201) | 012345678914 | WT Dan Tysk ,DT20 (3601201) | ZCS1 | 12345717 | 3,00_WT-BS01 3601201 Yearly Crane Inspec | 020 |  |  | CRANE | 1 | 2016-10-02 | REL NMAT SETC | ZBNQ PERF RECV RFCO | DE_OFFDT | ZMR1 | 0010 | Crane inspection | 3 | 1 | 3 | H | 0 | H | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-020 | WT DT20 DanTysk (3601201) | 012345678911 | WT Dan Tysk ,DT20 (3601201) | ZCS1 | 12345718 | 3,00_WT-BS01 3601201 Yearly Crane Inspec | 020 |  |  |  |  | 2016-10-02 | REL NMAT SETC | ZBNQ PERF RECV RFCO | DE_OFFDT | ZMR1 | 0020 | 3,00_WT-BS01 3601201 Yearly Crane Inspec | 3 | 1 | 3 | H | 0 | H | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 | 2017-09-01 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-012 | WT DT12 DanTysk (3601193) | 012345678912 | WT Dan Tysk ,DT12 (3601193) | ZCS5 | 12345719 | A9B10191123 - Retrofit, yaw software 201 | 040 |  |  |  |  | 2017-11-10 | REL CCOK MACM PRC SETC | ZBNQ PERF RECV ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10191123 - Retrofit, yaw software 201 | 0 | 0 | 0 | H | 0 | H | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_OFFDT | DB0388-012 | WT DT12 DanTysk (3601193) | 012345678913 | WT Dan Tysk ,DT12 (3601193) | ZCS5 | 12345720 | A9B10196140 Retrofit, sign f dehumidifi | 040 |  |  |  |  | 2017-11-10 | REL CCOK GMPS MACM PRC RESA SETC | ZBNQ PERF RFCO ZBCC | DE_OFFDT | ZMR1 | 0010 | A9B10196140 Retrofit, sign f dehumidifi | 0 | 0 | 0 | H | 0 | H | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-031 | WT SB32 Sandbank (4000362) | 012345678914 | WT Sandbank ,SB32 (4000362) | ZCS5 | 12345721 | Broken hose holder on pitch station tank | 040 | 2 | Normal |  |  | 2017-07-17 | REL CCOK MACM PRC SETC | ZBNQ PERF ZBA1 ZBPO | DE_SANDB | ZMR1 | 0010 | A# Broken hose holder on pitch stat.tank | 4 | 2 | 2 | H | 0 | H | 2017-07-17 | 2017-10-15 | 2017-07-17 | 2017-10-15 | 2017-07-17 | 2017-10-15 | 2017-07-17 | 2017-10-15 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-026 | WT SB26 Sandbank (4000357) | 012345678911 | WT Sandbank ,SB26 (4000357) | ZCS1 | 12345722 | TMSE: Exchange Fire Extinguishers | 020 | 3 | Low |  |  | 2017-08-29 | REL NMAT SETC | ZBNQ | DE_SANDB | ZMR1 | 0010 | TMSE: Exchange Fire Extinguishers | 0.5 | 1 | 0.5 | H | 0 | H | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 |  |  | REL
DE | 465C | BS01 | DE_SANDB | DB0411-065 | WT SB67 Sandbank (4000396) | 012345678912 | WT Sandbank ,SB67 (4000396) | ZCS5 | 12345723 | PT100 sensors possible swapped | 040 | 2 | Normal |  |  | 2017-08-29 | REL CCOK NMAT PRC SETC | ZBNQ PERF RFCO | DE_SANDB | ZMR1 | 0010 | PT100 sensors possible swapped | 4 | 2 | 2 | H | 0 | H | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 | 2017-08-25 | 2017-10-25 |  |  | REL
DE | 465C | BS01 | DE_OFFSB | DB0411-068 | WT SB76 Sandbank (4000399) | 012345678913 | WT Sandbank ,SB76 (4000399) | ZCS1 | 12345724 | WT-BS01 4000399 Service Maintenance | 020 |  |  | G4MK3R16 | 1 | 2017-03-21 | CRTD MANC NTUP SETC | ZBNQ | DE_S_ALL | ZSMC | 0010 | Jährlich | 118 | 2 | 59 | H | 0 | H | 2017-10-27 | 2017-10-27 |  |  | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  |  | CRTD
DE | 465C | BS01 | DE_OFFSB | DB0411-068 | WT SB76 Sandbank (4000399) | 012345678914 | WT Sandbank ,SB76 (4000399) | ZCS1 | 12345725 | WT-BS01 4000399 Service Maintenance | 020 |  |  | G4MK3R16 | 1 | 2017-03-21 | CRTD MANC NTUP SETC | ZBNQ | DE_OFFSB | ZMR1 | 0070 | 12 Monate (nur zur ersten jahreswartung) | 0 | 0 | 0 |  | 0 |  | 2017-10-27 | 2017-10-27 |  |  | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  |  | CRTD
DE | 465C | BS01 | DE_SANDB | DB0411-022 | WT SB22 Sandbank (4000353) | 012345678911 | WT Sandbank ,SB22 (4000353) | ZCS1 | 12345726 | TMSE: Echange Fire extinguisher | 020 | 3 | Low |  |  | 2017-09-06 | REL NMAT SETC | ZBNQ | DE_SANDB | ZMR1 | 0010 | TMSE: Echange Fire extinguisher | 1 | 1 | 1 | H | 0 | H | 2017-09-06 | 2017-11-06 | 2017-09-06 | 2017-11-06 | 2017-09-06 | 2017-11-06 | 2017-09-06 | 2017-11-06 |  |  | REL